## Region N RHP 2025 AP Primary
PRIORITY | Goal | Strategy # | Strategy Description | Primary/Driver | Advocate | Helper/Doer | unspecified | KPI Chosen | Next Steps | Priority | Status | Resources Needed | KPI Baseline and Date | Ownership/Source for KPI | KPI Goal | Collection Cadence (Monthly, Quarterly, Annually, Event Based?)
EQUITY AND RACIAL JUSTICE | Goal 1.2: Identify and advocate for modifications to policies and practices to remove barriers across the housing continuum for BIPOC, immigrants, migrants, refugees, people with disabilities, LGBTQ+, those with low incomes, and other marginalized populations. | 1.2.A | Identify and address redlining, exclusionary zoning, and other discriminatory policies and practices that result in inequities and residential segregation, including but not limited to appraisals, assessment of State Equalized Value, loan application denials, and insurance premiums. | 1 | 0 | 0 | 0 | Complete assessment of discriminatory policies and practices Establishment of advocacy / action plans | Identify sources of redlining, exclusionary zoning, and other discriminatory policies and practices throughout the region | Medium | Behind schedule | Technical Assistance | Needs to be established | Equity & Racial Justice Workgroup | Identify the why on gaps and build partnerships to fill the gaps | Needs to be established
EQUITY AND RACIAL JUSTICE | Goal 1.3: Increase the amount of housing that is accessible, safe, and healthy regardless of age, disability, or family size across all neighborhoods and communities. | 1.3.C | Incentivize increased numbers of accessible units, including for extremely low incomes, in new development projects. | 0 | 1 | 1 | 0 | # of new or refurbished accessible "universal design" units added to Region N housing stock | Identify driver of this strategy Connect with municipalities to discuss baseline Present strategy at potential Region N Landlord Summit | Low | Behind schedule |  | As of Q4 2023, connection with municipalities needs to occur to establish true baseline. | Equity & Racial Justice RHP Workgroup | Locate landlords and developers who are willing to work with special needs populations and large family needs. | Quarterly
PREVENTING AND ENDING HOMELESSNESS | Goal 3.1: Center equity for all and racial justice throughout the homelessness response system across Michigan. | 3.1.A | Create and implement a Racial Equity Strategic Plan to transform homeless service-delivery systems statewide by engaging and assessing the homeless and housing-service providers networks, creating shared learning, and engaging with people with lived experience. | 1 | 1 | 2 | 0 | Completion of Out-Wayne CoC Strategic Plan, currently in progress | Potential driver of this strategy: YHSI has a racial & gender equity analysis component that fits well here; although, it is for Transition Aged Youth. Any work affecting TAY should hopefully affect all populations so the YHSI team could possibly be the driver for this strategy | Medium | Behind schedule | Connection to detroit SP | Current plan last implemented in 2018 | Out-Wayne CoC Designee | To complete and implement updated Out-Wayne CoC strategic plan by Q1 (January 2024) | Event Based
PREVENTING AND ENDING HOMELESSNESS | Goal 3.1: Center equity for all and racial justice throughout the homelessness response system across Michigan. | 3.1.C | Evaluate and revise housing and service assessment tools, housing and resource prioritization, and screening policies and processes to center people that have been the most marginalized and impacted by discriminatory policies and practices. | Entry and Innovation Committee and Access & Prioritization Group | 2 | 1 | 0 | Completed Coordinated Entry & Resource Prioritization Evaluation | OW YHSI Team to present at next RHP Convening Q2 25 | High | Meeting this | Outreach & Education to greater community to recruit YAB | As of Q1 25 Out Wayne CoC awarded funds for assessment & prioritization grant for Youth Homeless Systems Improvement | Out-Wayne CoC, YHSI Team, Michelle Matchett & Kirstin Murphy | Create Regional and Local planning committees Create Regional and Local Youth Action Boards | Event Based with quarterly reporting
PREVENTING AND ENDING HOMELESSNESS | Goal 3.2: Increase access to stable and affordable quality housing options for households with extremely low incomes. | 3.2.A | Incentivize development of affordable and accessible housing units for households at or below 30% AMI to increase supply. | LLE team, OW CoC | 1 | 2 | 1 | # of developers attending workshops, stipulations in contracts stating they need to attend community engagement events. increase funds to diversify the programs needed to support these housing units | Identify driver of this strategy | High | Have not started | Add language to rental agreements, bring PHA to table | As of Q4 2023, Researching the current efforts the housing commission is currently doing | Housing Commissions, CoC | Increase landlord engagement/developer engagement; increased contracts for senior living, section 8, smaller community; maintenance needs be prioritized housing programs | Quarterly
PREVENTING AND ENDING HOMELESSNESS | Goal 3.2: Increase access to stable and affordable quality housing options for households with extremely low incomes. | 3.2.B | Invest in homelessness prevention and diversion efforts to keep households from entering shelter or staying in unsheltered situations in order to reduce trauma. | 0 | 1 | 1 | 1 | # of households diverted from shelter due to diversion efforts; increase diversion/support funds and offer more opportunities to apply for funds; be in partnership with landlords to increase accountability and work with individuals and families to do a rent payment plan; market value freeze in rent for individuals facing potential eviction | For youth - Prevention Demonstration Program NOFO is anticipated to be announced in 04-2025 | High | Behind schedule |  | As of Q4 2023, no such data is tracked, SSVF tracks program data--look into other agencies that track | Out-Wayne CoC Designee | # of families returning to use services | Quarterly
PREVENTING AND ENDING HOMELESSNESS | Goal 3.2: Increase access to stable and affordable quality housing options for households with extremely low incomes. | 3.2.C | Increase the supply of supportive housing units developed (including but not limited to recovery housing) by fully leveraging existing funding, expanding the pool of resources by soliciting new funding, and ensuring that those units are targeted to households in greatest need. | 0 | 1 | 1 | 1 | # of new and existing units; # of specific housing options; an updated list what funding exists currently and the barriers to accessing the funds | Identify driver of this strategy | Medium | Have not started |  | Research the current funds | RHP Workgroup | Grandfather in Section 8 housing to new generations after the HOH has passed, set up families to transition of the family homes and educate on what to do next; putting a skill into a client when they were not as supported | Monthly
PREVENTING AND ENDING HOMELESSNESS | Goal 3.2: Increase access to stable and affordable quality housing options for households with extremely low incomes. | 3.2.I | Utilize the Moving On initiative and MSHDA Housing Choice Voucher units data and include other related housing programs cross-system homelessness data-sharing and identify data-sharing protocols and infrastructure to ensure the state and local communities can collaboratively measure outcomes. | 0 | 1 | 0 | 0 | # of households in need of mitigation fund (includes HCV and other related housing programs) | YHSI has a data sharing component that may assist with this strategy - unsure if it will affect MOI & HCV specifically and it is a later phase in the project | Low | Have not started |  | What are the current # of vouchers available, how many are being utilized fully, what systems are currently utilized to track individuals looking for housing | Region N Task Force | Establish a data sharing system through existing efforts | Quarterly
PREVENTING AND ENDING HOMELESSNESS | Goal 3.3: Improve the quality of the homelessness response system to be client-centered, flexible, grounded in respect, trauma informed, and aware and inclusive of the cultural values, beliefs, and practices of those they serve. | 3.3.A | Increase funding for supportive housing services that are evidence-based, aligned with quality measures, and focused on tenant outcomes. | 1 | 3 | 2 | 2 | Establish a clause in funding that requires allocation of funds be set aside to cater to tenant outcomes in an evidence based method | Identify driver of this strategy | Medium | Meeting this |  | Data from those agencies that provide services, getting # on those who have been helped, long term tenet outcomes | Out-Wayne CoC Designee | Allocate funds effectively where needed; more preventative efforts need to be funded; education for tenants to support themselves after exiting the system | Annual
PREVENTING AND ENDING HOMELESSNESS | Goal 3.3: Improve the quality of the homelessness response system to be client-centered, flexible, grounded in respect, trauma informed, and aware and inclusive of the cultural values, beliefs, and practices of those they serve. | 3.3.B | Support organizations operating shelters to be low-barrier, focused on reducing harm, and trauma informed, including investing in infrastructure to de- congregate shelters. | 0 | 3 | 2 | 0 | # of non-congregate shelter beds available, shifting away from the # of existing congregate beds; # of culturally- competent trainings hosted by CoC for agencies receiving funding; | MCAH Training on disability and inclusion | High | Have not started | 1. Funding 2. Staff time 3. Access to information 4. Space 5. Political will 6. Collaboration | Research the total # beds of non-congregate available, congregate as well. | Out-Wayne CoC Designee | at least annual training; expand upon the resources to support those with mental and physical disabilities (e.g. identify acceptable shelter conditions for prioritized clients with disabilities) | Quarterly bed updates, Annual trainings
PREVENTING AND ENDING HOMELESSNESS | Goal 3.4: Increase cross-system partnerships to strengthen the homelessness response system, achieve greater housing stability, and impact social determinants of health. | 3.4.A | Develop referral linkages and tracking mechanisms between the CoCs and the McKinney-Vento school liaisons, workforce system partners, and income support services (e.g., SSI/SSDI, VA benefits) to strengthen coordination and streamline | 0 | 3 | 1 | 1 | # of referral partners between CoC and community resources, establish a referral system that's closed loop | Referral system with COC working with McKinney with Youth Homeless System improvements | High | Behind schedule | 1. Being creative with ways to receive support 2. Partnership support | Most commonly referred partners in the area, their referral processes' | RHP Workgroup, Region N Task Force, CoC | database that informs the community partners of an individual's referral status | Monthly
PREVENTING AND ENDING HOMELESSNESS | Goal 3.4: Increase cross-system partnerships to strengthen the homelessness response system, achieve greater housing stability, and impact social determinants of health. | 3.4.B | Support organizations operating shelters to be low-barrier, focused on reducing harm, and trauma informed, including investing in infrastructure to de-congregate shelters. | 0 | 3 | 2 | 0 | # of non-congregate shelter beds available, shifting away from the # of existing congregate beds; # of culturally-competent trainings hosted by CoC for agencies receiving funding; prioritize supporting those with mental/physical disabilities and provide resources for them after using the services | Identify driver of this strategy | Medium | Have not started |  | Research the total # beds of non-congregate available, congregate as well. | Out-Wayne CoC Designee / Coordinated Entry | at least annual training; expand upon the resources to support those with mental and physical disabilities (e.g. identify acceptable shelter conditions for prioritized clients with disabilities) | Quarterly bed updates, Annual trainings
HOUSING STOCK | Goal 4.1: Increase the supply of the full spectrum of housing that is affordable and attainable to Michigan residents. | 4.1.A | Advocate at the federal and state levels for increased funding, including gap funding, to support affordable and attainable housing ranging from small- to large-scale housing development. | 0 | 4 | 3 | 0 | # of presentations # of letters sent, buy-in and commitment; Creation of three single family homes to establish baseline for subsidy and have hard numbers for advocacy | 1. Wayne Metro CED 2. Evaluate new CEDAM gap funding Tool | Medium | Behind schedule | 1. Additional gap funding needed, ideally grants 2. Tool to convert brownfields: tax credit exchange |  | Identify driver of this strategy |  | Quarterly
HOUSING STOCK | Goal 4.5: Increase environmental sustainability, energy efficiency, and weatherization in housing rehabilitation and/or preservation. | 4.5.B | Foster better alignment between energy efficiency and weatherization programs, including emergency and critical repair. | 1 | 1 | 1 | 0 | # of homes with reduced energy costs | 1/3 of the way there | Medium | Meeting this | 1. Funding for rehabilitation (pre Wx & Ex) 2. Visibility of resources available |  | Wayne Metro Weatherization Team (DCC is also Subgrantee helping to drive this KPI) | 1000 Units by end of FY 26 | Quarterly
HOUSING STOCK | Missing Middle and Workforce Housing Goal 4.6: Increase missing middle and workforce housing stock to facilitate greater housing choice. | 4.6.A | Provide more incentives and fund income and appraisal gaps to support the development of missing middle housing types and workforce housing. | 1 | 1 | 1 | 0 | Research of potential area need and funding source | 1. Explore gaps funding CEDAM gap tool 2. Engage developers in engagement strategies | High | Meeting this |  | As of Q4 2023, need to research what materials already exist. | Driver: Downriver Community Conference and riverfront communities | Increase the availability and accessibility of housing stock for middle income households | Quarterly
HOUSING STOCK | Missing Middle and Workforce Housing Goal 4.6: Increase missing middle and workforce housing stock to facilitate greater housing choice. | 4.6.D | Develop a toolkit for organizations and companies that documents the advantages of employer-assisted housing fund programs and how to establish one in order to retain and attract talent. | 1 | 1 | 0 | 0 | Partner with MSHDA to host regional infosessoin on new $10 million Employer-Assisted Housing Fund, supported by FY25 state budget appropriations | Connect with MSHDA | Medium | Behind schedule |  | Provide local TA and resources for employee assisted housing fund | Housing Stock RHP Workgroup | Conduct at least one info session; continue to push relevant information to Region N | Event based
HOUSING STOCK | Zoning Goal 4.7: Expand the use of equitable and holistic local planning and zoning practices to increase housing supply. | 4.7.A | Provide capacity in the form of housing-related technical support for smaller municipalities. | 1 | 0 | 1 | 0 | Shared, dedicated technical assistance and ongoing training at MSHDA with staff assigned at a regional level | 1. Outreach to MAP 2. Advance/execute the zoning atlas | High | Meeting this | Existing MAP resources |  | Someone in the development as well as non-profit communities. Also need state representatives in the conversation. Need to make sure we have county representation in the conversation as well. More of a collective voice(advisorship/partnership). A taskforce of sorts | Specific TA areas are provided to support with less experienced developers, property types and municipalities. Sponsor educational classes at a given frequency and make sure that is is accessible to all regions. | Quarterly
HOUSING STOCK | Zoning Goal 4.7: Expand the use of equitable and holistic local planning and zoning practices to increase housing supply. | 4.7.D | Develop model language for zoning amendments or overlays that remove obstacles to increasing the housing supply. | 0 | 1 | 1 | 0 | Creation & initiating use of a "user friendly" reference document for zoning and ordinance language to increase flexibility that increases housing stock in a given region | TA Provider to: 1. Gather and distribute existing language 2. Gather feedback 3. Finalize and adopt doc 4. Outreach to MAP 5. Advance/execute the zoning atlas | High | Meeting this |  | American Planners Association - may have document already Q4 2023- Review and distribute APA and other relevant material to 2 pilot municipalities and ensure feedback is provided on success of converting reference document to zoning changes/project approvals/overlays | Wayne Metro and Housing Stock Workgroup | Distribution of this resource. Have cities adopt this as a resource. Create flexibility for developers and municipalities to work together to create housing stock. Make sure organizations are educated on zoning, restrictions and exceptions Feedback from municipalities are incorporated in model language by the end of the next rolling quarter #of projects that fit the model must be reported quarterly # of municipalities that are providing feedback on model language must increase quarterly | Quarterly
RENTAL HOUSING | Goal 6.1: Keep people housed by reducing the number of evictions. | 6.1.A | Encourage early-intervention eviction-diversion and referral programming at the community level that engages landlords, property managers, tenants, utilities, and community service providers to identify those who are at risk before court action is needed, and if unavoidable, increase access to legal services for tenants in eviction proceedings. | 0 | 0 | 4 | 0 | Create and cultivate a program to help bridge the gap between receiving notice and final eviction; promote the establishment of Right to Counsel programs in Out-Wayne County CoC communities | 1. Landlord engagement/social media 2. Standardize COC registration 3. Landlord/tenant education | High | Have not started |  | Research City of Detroit Right to Counsel |  |  | Semi-Annual
RENTAL HOUSING | Goal 6.2: Reduce the number of underserved and vulnerable populations experiencing rent burden by removing barriers and increasing resources. | 6.2.A | Develop programs with landlords and their trade associations to remove barriers and provide incentives (e.g ., screening criteria, rent guarantees). | 1 | 0 | 2 | 1 | Develop landlord advisory group for affordable housing | Property upkeep training for both tenant and landlords - Host LL summit or roundtable | High | Behind schedule |  | Landlord Summit/Roundtable | Kimberly Young, Landlord | Landlord advisory group established by Q2 2024 | Semi-Annual
RENTAL HOUSING | Goal 6.2: Reduce the number of underserved and vulnerable populations experiencing rent burden by removing barriers and increasing resources. | 6.2.E | Establish a statewide housing mobility program targeted particularly to Housing Choice Voucher tenant participants and prospective landlords, including affordable supportive services and incentives for landlords renting properties in mixed-income areas. | 1 | 1 | 2 | 0 | Creation of statewide waitlist for housing choice voucher program Engage other RHP Regions to research if a priority and buy-in that already exists. | 1. Survey Public Housing Authorities 2. Meet with MSHDA Section 8 3. Develop Case Studies/Benchmarking | High | Meeting this |  | As of Q1 25 Precedent for this strategy is twofold 1. This practice is active in Massachusetts and Maine; 2. MSHDA utilized a single statewide waiting list for the CERA program. | Westland Housing in Region - MSHDA as eventual holder of waitlist | Make connections with other Housing Commissions and RHP regional leads to build partnership statewide (i.e. 5 meetings with other RHPs, housing commissions, etc) Completed by end of 2023 | Monthly
COMMUNICATION AND EDUCATION | Goal 8.2: Increase inclusive education and awareness of existing housing programs and services in the state. | 8.2.A | Ensure that Michigan's 2-1-1 system has up-to-date information about housing assistance (e.g., payment assistance, weatherization supports, etc.). | Wayne Metro/Out Wayne CoC | 1 | 1 | 0 | 1. # of individuals engaged (211, info center, WM) 2. # of partner orgs engaged | Creation of a plan to enhance collaboration between 211 and The Information Center (along with other Out-Wayne Call Centers) Ensure up to date information through mending the safety net events and bi-annual updates Wayne County HHVS is developing an all inclusive public health resource guide working with 211 for Wayne County Specifically, including Detroit. Bring a WM Community Outreach team member to these events moving forward Wayne County HHVS can help push outreach Identify leaders at each organization to push informaiton for email blasts Develop a shared event calendar with each organization hosting information days or customer assistance days | Medium | Behind schedule |  | As of Q4 24, no such plan/group exists | Communication & Education Workgroup | # of entities providing information to call centers and/or updating existing information and programming to call centers | Quarterly
COMMUNICATION AND EDUCATION | Goal 8.2: Increase inclusive education and awareness of existing housing programs and services in the state. | 8.2.B | Increase awareness among housing providers and those who provide assistance of the programs and services available | Wayne Metro/Out Wayne CoC | 1 | 1 | 0 | 1. # of exhibitors of various social determinants of health present 2. diversity of industry present at events | Create a "Mending the Safety Net" event | Low | Have not started |  | # of individuals engaged through Mending Safety net event and # of partner orgs present, have someone from the information center present and 211 to engage and communicate what programs are available. | Communication & Education Workgroup | Host "mending the safety net" event | Event based
COMMUNICATION AND EDUCATION | Goal 8.2: Increase inclusive education and awareness of existing housing programs and services in the state. | 8.2.C | Increase awareness of the process for qualifying, enrolling, and obtaining local- and state-subsidized housing, including waiting lists, among those needing assistance. | Wayne Metro/Out Wayne CoC | 1 | 0 | 0 | Creation of a plan to promote awareness of programming and resources in Region N Creation of a public facing guide to housing programs | Identify driver of this strategy | High | Have not started |  | As of Q4 24, no such plan/group exists | Communication & Education Workgroup | # of unique callers / website access for information regarding programming | Quarterly